DfE School Led Tutoring Grant: summary

| Total number of pupils: | 44 at Admiral Long / 76 at Birstwith |
| --- | --- |
| Total catch-up premium budget: | £2,024 |

strategy statement

- The collaboration strategy is based upon supporting those children whose learning, due to lockdown, has significantly suffered and as such they have fallen behind where the school would ordinarily expect them to be had they remained in school throughout. This strategy will demonstrate how the collaboration has identified those children in need of additional support, how that support will be delivered and what the impact of the support will be. It must be noted that children who have been identified as requiring additional support are not specifically children with SEND.

Barriers to learning

- Barriers to learning in our collaboration include (but not exclusively):

- Poor parental input / support during lockdown

- Lack of working memory capacity

- Losing the support of a regular routine

- Anxiety surrounding COVID and the impact it may have on their and their family member’s health

- Lack of availability of technology at home – eg. parents need their own devices for their own work

- Reduction in challenge of work sent home – work had to be set that could be done independently by the children to allow parents to work

- Lack of skill in parents to deliver quality lessons

| barriers to future attainment |  |
| --- | --- |
| - Academic barriers: |  |
| - A | Some children managed to maintain expected standards whereas others did not, so lesson content has to be adapted to ensure all children access learning. This has widened the attainment gap in not just the core subjects but in all subjects. |
| B | An adapted curriculum based on online content has reduced our ability as a school to provide a bespoke and personalised curriculum as was the case before lockdown. |
| C | Seating arrangements in classrooms mean that children cannot collaborate or share ideas as they once did and teachers cannot access groups and offer support to the depth and detail as they did prior to lockdown. |

| ADDITIONAL BARRIERS |  |
| --- | --- |
| External barriers: |  |
| D | Continued anxiety around COVID and its impact on the physical and mental health of children |
| E | Continued anxiety around COVID and its impact on people’s economic wealth |
| F | Children remaining at home due to self-isolation, |
| G | Lack of IT at home due to parents working from home and needing the devices |
| H | Continued lack of support at home due to ‘key-worker’ parents working and not being able to teach their children during periods of self-isolation |

Planned expenditure for current academic year

| Quality of teaching for all |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Action | Intended outcome and success criteria | - What’s the evidence and rationale for this choice? | - How will you make sure it’s implemented well? | - Staff lead | - When will you review this? |
| Week 1 – 5 Assessment of children’s mental health and well-being – are they ready to be in school and ready to learn? | Establish that the children are well and ready to learn All children are happy and safe and ready to learn | - It was felt that we had to establish that the children were in the right frame of mind once they returned after such a lengthy absence. The first three weeks, although were very much spent taking part in re-integration activities to ensure that the children were ready to learn again, were back to a full, ambitious curriculum in order to maximise learning time following a period of absence. | Staff met regularly to discuss concerns that their children may generate during pupil progress meetings which focused specifically on the mental health of the children rather than the loss of academic progress | Executive Headteacher | October 2021 |
| Week 5 – 6 Assessment week and review | All children completed summer 2021 assessments in reading and maths (NfER) assessments and TA for writing as a baseline so future progress can be tracked accurately | The best indicator of the where the children were, was to accurately assess them on the summer tests in the autumn term. The delay in doing so was to ensure that the children were settled before they were tested | Tests were conducted in all year groups to provide a baseline and a target group of children who could easily be identified as requiring additional support in the core subjects. | Executive Headteacher | October 2021 |
| Total budgeted cost: |  |  |  |  | £0 |
| Targeted support |  |  |  |  |  |
| Action | Intended outcome and success criteria | - What’s the evidence and rationale for this choice? | - How will you make sure it’s implemented well? | - Staff lead | - When will you review this? |
| Week 1-14 | Year 6 children to take part in 1:1/2:1 small group intervention from a recognised National Tutoring Partner – Protocol Education | In order for children to close any knowledge learning gaps as a result of the pandemic, it was felt that an external provider would be best placed to provide tuition as opposed to ‘in-school’ staff who were very much class-based in order to reestablish learning routines. | Monitor the quality of tutoring. Ensure the same tutor each week, across the collaboration in order to provide consistency or personnel for the children – developing relationships to ensure positive impact. | Executive Headteacher | December 2021. |
| Week 1-14 | Additional intervention from exisiting school staff. Those children identified as requiring additional catch up support will catch up with where we expect them to be | Those children who had been identified work better with people who know them – their class teachers/teaching assistants could provide them with what they specifically needed rather than having to explain to an tutor | Class teachers have planned additional teaching assistant/tutor sessions for the and are able to provide additional and different support to the target groups. This is implemented well, as teachers know immediately what their children need because of knowing them so well – what the children did not understand/misconceptions from lockdown can be addressed. | NC | December 2021 February 2022 March 2022 £0 |
| Total budgeted cost: |  |  |  |  | £2024 |

*Note – The total for Autumn Term Tutoring across the collaboration was £3651.00

additional information

- We have a robust Assessment Schedule carrying out assessments six times a year to inform our pupil’s progress in reading and maths. Data acquired from the results of these assessments are submitted into a spreadsheet on the NfER Portal, Steps 2 Success Assessment Tracker, Little Wandle Tracker. - We use Teacher Assessment throughout to inform our pupil’s progress in reading, writing and maths.